## Work Plan
Phase | PhaseName | Sub | Task | Hrs | Cost | Deliverable | Assigned
0 | System Architecture & Interface Definition | 0.1 | GPIO pinout & topology freeze | 6 | 210 | Zero GPIO conflicts. Single ESP32-S3 pin assignment sheet signed off. | Robotics Firmware Engineer
0 | System Architecture & Interface Definition | 0.2 | FreeRTOS task map & core pinning | 5 | 175 | All 15 tasks defined: core, priority, stack, period. Queue specs signed off. | Robotics Firmware Engineer
0 | System Architecture & Interface Definition | 0.3 | Safety boundaries & CAN bus isolation | 5 | 175 | 4-layer defense model, ESTOP bypass paths, mode state machine signed off. | Robotics Firmware Engineer
1 | Protocol & Bench Bring-up | 1.1 | CAN physical layer bench setup | 6 | 210 | Clean CAN frames on PC analyzer, zero errors over 10 min. | Integration/Test Engineer
1 | Protocol & Bench Bring-up | 1.2 | Steer-by-Wire (SES) actuation discovery | 8 | 280 | Rack moves to commanded angle. CAN ID, payload layout, angle scaling documented. | Integration/Test Engineer
1 | Protocol & Bench Bring-up | 1.3 | Steer-by-Wire (SES) feedback decoding | 6 | 210 | Feedback CAN IDs decoded: angle, faults, center status. ±0.5° accuracy verified. | Integration/Test Engineer
1 | Protocol & Bench Bring-up | 1.4 | Brake-by-Wire (SEB) actuation & venting discovery | 8 | 280 | Pressure >2 MPa via CAN. Vent sequence, pressure scaling, stroke limits documented. | Integration/Test Engineer
1 | Protocol & Bench Bring-up | 1.5 | Brake-by-Wire (SEB) feedback decoding | 6 | 210 | Feedback CAN IDs decoded: pressure, stroke, fault codes. ±5% gauge match. | Integration/Test Engineer
2 | CAN Dictionary & Protocol Definition | 2.1 | Public bus CAN message formalization | 4 | 140 | All 10 public CAN IDs documented: field offsets, types, scaling, rates. Bus load <5%. | Robotics Firmware Engineer
2 | CAN Dictionary & Protocol Definition | 2.2 | Private bus (Syntree) CAN message formalization | 4 | 140 | All Syntree IDs formalized from Phase 1 data: byte layouts, scaling, checksums, fault tables. | Robotics Firmware Engineer
2 | CAN Dictionary & Protocol Definition | 2.3 | Update can_protocol.h from CAN dictionary | 2 | 70 | can_protocol.h matches dictionary. All struct sizes pass static_assert. | Robotics Firmware Engineer
3 | Core Firmware Platform Development | 3.1 | Unified project structure & build system | 4 | 140 | pio run succeeds, zero warnings. Single firmware image. shared/intermcu/ removed. | Robotics Firmware Engineer
3 | Core Firmware Platform Development | 3.2 | FreeRTOS task creation & core pinning | 4 | 140 | All 15 tasks running on correct cores. No stack overflow. Syntree tasks stubbed. | Robotics Firmware Engineer
3 | Core Firmware Platform Development | 3.3 | Queue & atomic plumbing | 3 | 105 | can_rx_queue(16), cmd_queue(4), setpoint_queue(4). g_mode atomic. No overflows. | Robotics Firmware Engineer
3 | Core Firmware Platform Development | 3.4 | Dual-CAN driver init & heartbeat | 3 | 105 | 0x7FF @ 2 Hz, 0x011 @ 5 Hz on public bus. Private bus initialized, silent. | Robotics Firmware Engineer
4 | Vehicle I/O & State Estimation | 4.1 | PCNT encoder → speed estimation | 5 | 175 | Speed mm/s ±5% of known RPM. CAN 0x120 @ 100 Hz. EMA filter stable ±2%. | Robotics Firmware Engineer
4 | Vehicle I/O & State Estimation | 4.2 | I2C IMU → yaw rate | 3 | 105 | Yaw rate ±10% of known rotation. Drift <1°/s stationary after calibration. | Robotics Firmware Engineer
4 | Vehicle I/O & State Estimation | 4.3 | Throttle ADC & mode switch | 3 | 105 | Speed linear across range, 200-count dead zone. Mode switch toggles Manual/Auto. | Robotics Firmware Engineer
4 | Vehicle I/O & State Estimation | 4.4 | HC-SR04 obstacle sensor & heartbeat timing | 3 | 105 | Distance ±3 cm at 0.5/1/2 m. CAN 0x400 @ 10 Hz. Timeout → UINT32_MAX. | Robotics Firmware Engineer
5 | Physics Model & Command Resolution | 5.1 | Inverse bicycle model kinematics | 5 | 175 | Unit tests pass. Slew 180°/s, low-speed freeze at 50 mm/s, ±45° clamp. | Robotics Firmware Engineer
5 | Physics Model & Command Resolution | 5.2 | Reverse & direction logic | 2 | 70 | Reverse cap −500 mm/s. Direction sign correct. 0x210 reversing flag verified. | Robotics Firmware Engineer
5 | Physics Model & Command Resolution | 5.3 | Obstacle speed limiting | 3 | 105 | Stop at 300 mm, clear at 3000 mm, linear ramp between. Smooth transitions verified. | Robotics Firmware Engineer
5 | Physics Model & Command Resolution | 5.4 | End-to-end command resolution test | 2 | 70 | Synthetic 0x300 → bounded setpoints. No NaN/overflow over 1-hour run. | Robotics Firmware Engineer
6 | Safety Architecture & Fail-safe Control | 6.1 | E-stop detection & hardware relay | 4 | 140 | <1 ms GPIO edge → PWM=0V. Hardware NC relay opens ~10 ms. CAN 0x001 also triggers. | Robotics Firmware Engineer
6 | Safety Architecture & Fail-safe Control | 6.2 | Brake lever & max-select arbitration | 3 | 105 | 3-input max: E-stop/lever/CAN 0x301. Each triggers independently. Release → off. | Robotics Firmware Engineer
6 | Safety Architecture & Fail-safe Control | 6.3 | Heartbeat timeout & command staleness watchdog | 3 | 105 | HB timeout 1500 ms → ESTOP. 0x300 stale 200 ms → setpoint zero. Logic analyzer verified. | Robotics Firmware Engineer
6 | Safety Architecture & Fail-safe Control | 6.4 | ESTOP bypass paths & external watchdog | 4 | 140 | Switch cannot exit ESTOP. GPIO21 stuck → MCU reset <100 ms. Post-reset: Manual, safe. | Robotics Firmware Engineer
7 | Motion Control & Actuation | 7.1 | PID speed controller | 6 | 210 | Kp=1.0 Ki=0.1 Kd=0.05. Overshoot <20%, settle <500 ms. Anti-windup clamp ±500. | Robotics Firmware Engineer
7 | Motion Control & Actuation | 7.2 | Motor effort output (PWM) | 3 | 105 | 20 kHz PWM on GPIO 6, DIR on GPIO 7. ESTOP forces zero. Oscilloscope verified. | Robotics Firmware Engineer
7 | Motion Control & Actuation | 7.3 | Ingest Phase 2 CAN dictionary (private bus) | 3 | 105 | All private-bus IDs, structs, configs match Phase 2 dictionary. No stub code remains. | Robotics Firmware Engineer
7 | Motion Control & Actuation | 7.4 | Steering & brake CAN command generation | 4 | 140 | 0x169 steering, SEB brake via CAN. E-stop/lever/0x301 → SEB. GPIO14/18 fallback only. | Robotics Firmware Engineer
7 | Motion Control & Actuation | 7.5 | Syntree status monitoring & fault response | 2 | 70 | EPS/SEB fault → ESTOP within feedback timeout. All fault codes decoded correctly. | Robotics Firmware Engineer
8 | Firmware Bring-up & Operator Modes | 8.1 | Manual mode bench test | 3 | 105 | Throttle → motor linear. Brake lever engages. Obstacle publishes but does not limit. | Robotics Firmware Engineer
8 | Firmware Bring-up & Operator Modes | 8.2 | Auto mode bench test (CAN-injected commands) | 4 | 140 | 0x300 → motor + steering + brake. 0x301 → SEB. All telemetry frames decode correctly. | Robotics Firmware Engineer
8 | Firmware Bring-up & Operator Modes | 8.3 | Mode transition testing | 3 | 105 | All transitions per state machine. ESTOP lockout. Power-cycle → Manual (safe default). | Robotics Firmware Engineer
9 | ROS 2 Integration | 9.1 | SocketCAN bridge foundation | 6 | 210 | Bidirectional CAN on Jetson. No dropped frames over 30 min. PC analyzer match. | Robotics Firmware Engineer
9 | ROS 2 Integration | 9.2 | /cmd_vel → 0x300 serialization | 5 | 175 | Twist → big-endian i32 speed + i32 yaw. Boundary values serialize correctly. | Robotics Firmware Engineer
9 | ROS 2 Integration | 9.3 | 0x301 brake publisher | 3 | 105 | ros2 topic pub → 0x301 on CAN → SEB engages at commanded pressure. | Robotics Firmware Engineer
9 | ROS 2 Integration | 9.4 | Telemetry → /odom | 8 | 280 | 0x210/0x220/0x400 → nav_msgs/Odometry @ 10 Hz. Matches live ESP32 state. | Robotics Firmware Engineer
9 | ROS 2 Integration | 9.5 | Diagnostics → /diagnostics | 5 | 175 | 0x011/0x600 → DiagnosticArray @ 1 Hz. ERROR status on ESTOP or CAN faults. | Robotics Firmware Engineer
9 | ROS 2 Integration | 9.6 | Keyboard teleop | 5 | 175 | i=forward ,=reverse j/l=turn k=stop ESC=E-stop. ±3000 mm/s, ±785 mrad/s limits. | Robotics Firmware Engineer
10 | Integration, Validation & Tuning | 10.1 | Multi-node soak & CAN health | 6 | 210 | 2-hour run: zero queue overflows, TEC/REC=0, heap stable, 0% frame drop. | Robotics Firmware Engineer
10 | Integration, Validation & Tuning | 10.2 | State machine validation | 6 | 210 | All transitions verified. ESTOP lockout. Power-cycle → Manual. Video recorded. | Robotics Firmware Engineer
10 | Integration, Validation & Tuning | 10.3 | On-vehicle PID & steering tuning | 8 | 280 | ±10% steady-state error. Smooth steering. Obstacle stop <350 mm. Encoder calibrated. | Robotics Firmware Engineer
10 | Integration, Validation & Tuning | 10.4 | Fault injection | 8 | 280 | 7 fault scenarios: all → safe halt. No runaway. No CAN lockup. Video recorded. | Robotics Firmware Engineer
10 | Integration, Validation & Tuning | 10.5 | Endurance & road test | 2 | 70 | 30 min Auto-mode drive. Zero safety violations. No telemetry gaps. Connectors secure. | Robotics Firmware Engineer
TOTAL |  |  |  | 204 | 7140
TOTAL |  |  |  | 204 | 7140
TOTAL |  |  |  | 204 | 7140